## Financial Proj
Housing | 7/2012 | 10/2012 | 1/2013 | 4/2013 | 7/2013 | 10/2013 | 1/2014 | 4/2014 | 7/2014 | 10/2014 | 1/2015 | 4/2015 | 7/2015 | 10/2015 | 1/2016 | 4/2016 | 7/2016 | 10/2016 | 1/2017 | 4/2017 | 7/2017 | 10/2017 | 1/2018 | 4/2018 | 7/2018 | 10/2018 | 1/2019 | 4/2019 | 7/2019 | 10/2019 | 1/2020 | 4/2020 | 7/2020 | 10/2020 | 1/2021 | 4/2021 | 7/2021 | 10/2021 | 1/2022 | 4/2022 | 7/2022
Projected Expenditures | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88640 | 88640 | 88640 | 130846 | 182781 | 182781 | 177116 | 177116 | 219906 | 219906 | 219906 | 219906 | 220033 | 220033 | 301933 | 323033 | 323033 | 323033 | 323033 | 345872.5 | 373280.63 | 397302.63 | 397302.63 | 397302.63 | 397302.63 | 397302.63 | 397302.63 | 441562.03 | 485821.43 | 530080.83 | 574340.23 | 618599.63 | 618599.63 | 618599.63
Quarterly Projection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88640 | 0 | 0 | 42206 | 51935 | 0 | -5665 | 0 | 42790 | 0 | 0 | 0 | 127 | 0 | 81900 | 21100 | 0 | 0 | 0 | 22839.5 | 27408.13 | 24022 | 0 | 0 | 0 | 0 | 0 | 44259.4 | 44259.4 | 44259.4 | 44259.4 | 44259.4 | 0 | 0
Actual Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88640.38 | 88640.38 | 88640.38 | 130846.41 | 182781.53 | 182781.53 | 177116.43 | 177116.43 | 219906.33 | 219906.33 | 219906.33 | 219906.33 | 220033.5 | 220033.5 | 301933.5 | 323033.5 | 323033.5 | 323033.5 | 323033.5 | 345873 | 373281.13 | 397303.13 | 397303.13 | 397303.13 | 397303.13 | 397303.13 | 397303.13 | 397303.13 | 397303.13 | 397303.13 | 397303.13 | 397303.13 | 397303.13 | 397303.13
Actual Quarterly Expend (from QPRs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88640.38 | 0 | 0 | 42206.03 | 51935.12 | 0 | -5665.1 | 0 | 42789.9 | 0 | 0 | 0 | 127.17 | 0 | 81900 | 21100 | 0 | 0 | 0 | 22839.5 | 27408.13 | 24022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Projects | 7/2012 | 10/2012 | 1/2013 | 4/2013 | 7/2013 | 10/2013 | 1/2014 | 4/2014 | 7/2014 | 10/2014 | 1/2015 | 4/2015 | 7/2015 | 10/2015 | 1/2016 | 4/2016 | 7/2016 | 10/2016 | 1/2017 | 4/2017 | 7/2017 | 10/2017 | 1/2018 | 4/2018 | 7/2018 | 10/2018 | 1/2019 | 4/2019 | 7/2019 | 10/2019 | 1/2020 | 4/2020 | 7/2020 | 10/2020 | 1/2021 | 4/2021 | 7/2021 | 10/2021 | 1/2022 | 4/2022 | 7/2022
Projected Expenditures | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41318 | 41318 | 41318 | 73002 | 110174 | 110174 | 148084 | 148084 | 284582 | 676889 | 864645 | 1010025 | 1201254 | 1249579 | 1272809 | 1302385 | 1308333 | 1402617 | 1508673 | 1815355 | 1824184 | 2373163 | 2373163 | 2373163 | 2373163 | 2373163 | 3291990 | 4000937.96 | 4709885.92 | 5418833.88 | 6127781.84 | 6836729.8 | 6836729.8 | 6836729.8
Quarterly Projection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41318 | 0 | 0 | 31684 | 37172 | 0 | 37910 | 0 | 136498 | 392307 | 187756 | 145380 | 191229 | 48325 | 23230 | 29576 | 5948 | 94284 | 106056 | 306682 | 8829 | 548979 | 0 | 0 | 0 | 0 | 918827 | 708947.96 | 708947.96 | 708947.96 | 708947.96 | 708947.96 | 0 | 0
Actual Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41317.67 | 41317.67 | 41317.67 | 73002.02 | 110173.94 | 110173.94 | 148083.71 | 148083.71 | 284581.89 | 676888.96 | 864644.95 | 1010025.39 | 1201253.93 | 1249579.37 | 1272809.51 | 1302385.74 | 1308333.98 | 1402617.71 | 1508673.58 | 1815355.37 | 1824184.28 | 2373163.1 | 2373163.1 | 2373163.1 | 2373163.1 | 2373163.1 | 3291989.96 | 3291989.96 | 3291989.96 | 3291989.96 | 3291989.96 | 3291989.96 | 3291989.96 | 3291989.96
Actual Quarterly Expend (from QPRs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41317.67 | 0 | 0 | 31684.35 | 37171.92 | 0 | 37909.77 | 0 | 136498.18 | 392307.07 | 187755.99 | 145380.44 | 191228.54 | 48325.44 | 23230.14 | 29576.23 | 5948.24 | 94283.73 | 106055.87 | 306681.79 | 8828.91 | 548978.82 | 0 | 0 | 0 | 0 | 918826.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Planning & Admin | 7/2012 | 10/2012 | 1/2013 | 4/2013 | 7/2013 | 10/2013 | 1/2014 | 4/2014 | 7/2014 | 10/2014 | 1/2015 | 4/2015 | 7/2015 | 10/2015 | 1/2016 | 4/2016 | 7/2016 | 10/2016 | 1/2017 | 4/2017 | 7/2017 | 10/2017 | 1/2018 | 4/2018 | 7/2018 | 10/2018 | 1/2019 | 4/2019 | 7/2019 | 10/2019 | 1/2020 | 4/2020 | 7/2020 | 10/2020 | 1/2021 | 4/2021 | 7/2021 | 10/2021 | 1/2022 | 4/2022 | 7/2022
Projected Expenditures | 0 | 14612 | 35137 | 35137 | 99693 | 190645 | 288122 | 280763 | 280763 | 280763 | 285576 | 291185 | 291185 | 291185 | 291185 | 291185 | 293188 | 293188 | 293188 | 303439 | 303712 | 303982 | 316544 | 316544 | 316544 | 316544 | 337699 | 345617 | 349427 | 349427 | 349427 | 349427 | 349427 | 351156 | 392254.2 | 392254.2 | 392254.2 | 392254.2 | 392254.2 | 392254.2 | 392254.2
Quarterly Projection | 0 | 14612 | 20525 | 0 | 64556 | 90952 | 97477 | -7359 | 0 | 0 | 4813 | 5609 | 0 | 0 | 0 | 0 | 2003 | 0 | 0 | 10251 | 273 | 270 | 12562 | 0 | 0 | 0 | 21155 | 7918 | 3810 | 0 | 0 | 0 | 0 | 1729 | 41098.2 | 0 | 0 | 0 | 0 | 0 | 0
Actual Expenditure | 0 | 14612.19 | 35137.15 | 35137.15 | 99693.07 | 190645.12 | 288121.83 | 280762.67 | 280762.67 | 280762.67 | 285576.16 | 291185.14 | 291185.14 | 291185.14 | 291185.14 | 291185.14 | 293187.81 | 293187.81 | 293187.81 | 303438.36 | 303711.78 | 303981.28 | 316543.24 | 316543.24 | 316543.24 | 316543.24 | 337698.47 | 345616.53 | 349426.36 | 349426.36 | 349426.36 | 349426.36 | 349426.36 | 351155.74 | 351155.74 | 351155.74 | 351155.74 | 351155.74 | 351155.74 | 351155.74 | 351155.74
Actual Quarterly Expend (from QPRs) | 0 | 14612.19 | 20524.96 | 0 | 64555.92 | 90952.05 | 97476.71 | -7359.16 | 0 | 0 | 4813.49 | 5608.98 | 0 | 0 | 0 | 0 | 2002.67 | 0 | 0 | 10250.55 | 273.42 | 269.5 | 12561.96 | 0 | 0 | 0 | 21155.23 | 7918.06 | 3809.83 | 0 | 0 | 0 | 0 | 1729.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Expenditures | 7/2012 | 10/2012 | 1/2013 | 4/2013 | 7/2013 | 10/2013 | 1/2014 | 4/2014 | 7/2014 | 10/2014 | 1/2015 | 4/2015 | 7/2015 | 10/2015 | 1/2016 | 4/2016 | 7/2016 | 10/2016 | 1/2017 | 4/2017 | 7/2017 | 10/2017 | 1/2018 | 4/2018 | 7/2018 | 10/2018 | 1/2019 | 4/2019 | 7/2019 | 10/2019 | 1/2020 | 4/2020 | 7/2020 | 10/2020 | 1/2021 | 4/2021 | 7/2021 | 10/2021 | 1/2022 | 4/2022 | 7/2022
Projected Expenditures | 0 | 14612 | 35137 | 35137 | 99693 | 190645 | 288122 | 410721 | 410721 | 410721 | 489424 | 584140 | 584140 | 616385 | 616385 | 795673 | 1189983 | 1377739 | 1523119 | 1724726 | 1773324 | 1878724 | 1941962 | 1947910 | 2042194 | 2148250 | 2498926.5 | 2543081.63 | 3119892.63 | 3119892.63 | 3119892.63 | 3119892.63 | 3119892.63 | 4040448.63 | 4834754.19 | 5587961.55 | 6341168.91 | 7094376.27 | 7847583.63 | 7847583.63 | 7847583.63
Quarterly Projection | 0 | 14612 | 20525 | 0 | 64556 | 90952 | 97477 | 122599 | 0 | 0 | 78703 | 94716 | 0 | 32245 | 0 | 179288 | 394310 | 187756 | 145380 | 201607 | 48598 | 105400 | 63238 | 5948 | 94284 | 106056 | 350676.5 | 44155.13 | 576811 | 0 | 0 | 0 | 0 | 920556 | 794305.56 | 753207.36 | 753207.36 | 753207.36 | 753207.36 | 0 | 0
Actual Expenditure | 0 | 14612.19 | 35137.15 | 35137.15 | 99693.07 | 190645.12 | 288121.83 | 410720.72 | 410720.72 | 410720.72 | 489424.59 | 584140.61 | 584140.61 | 616385.28 | 616385.28 | 795673.36 | 1189983.1 | 1377739.09 | 1523119.53 | 1724725.79 | 1773324.65 | 1878724.29 | 1941962.48 | 1947910.72 | 2042194.45 | 2148250.32 | 2498926.84 | 2543081.94 | 3119892.59 | 3119892.59 | 3119892.59 | 3119892.59 | 3119892.59 | 4040448.83 | 4040448.83 | 4040448.83 | 4040448.83 | 4040448.83 | 4040448.83 | 4040448.83 | 4040448.83
Actual Quarterly Expend (from QPRs) | 0 | 14612.19 | 20524.96 | 0 | 64555.92 | 90952.05 | 97476.71 | 122598.89 | 0 | 0 | 78703.87 | 94716.02 | 0 | 32244.67 | 0 | 179288.08 | 394309.74 | 187755.99 | 145380.44 | 201606.26 | 48598.86 | 105399.64 | 63238.19 | 5948.24 | 94283.73 | 106055.87 | 350676.52 | 44155.1 | 576810.65 | 0 | 0 | 0 | 0 | 920556.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Performance Proj
Demolition & Debris Removal | 7/2012 | 10/2012 | 1/2013 | 4/2013 | 7/2013 | 10/2013 | 1/2014 | 4/2014 | 7/2014 | 10/2014 | 1/2015 | 4/2015 | 7/2015 | 10/2015 | 1/2016 | 4/2016 | 7/2016 | 10/2016 | 1/2017 | 4/2017 | 7/2017 | 10/2017 | 1/2018 | 4/2018 | 7/2018 | 10/2018 | 1/2019 | 4/2019
Projected Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 15 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
# of Housing Units (Quarterly Projection) | 0 | [6 empty] | 5 | 10 | 5
Actual Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
# of Housing Units (Populated from QPR Reporting) | 0
Home Purchase | 7/2012 | 10/2012 | 1/2013 | 4/2013 | 7/2013 | 10/2013 | 1/2014 | 4/2014 | 7/2014 | 10/2014 | 1/2015 | 4/2015 | 7/2015 | 10/2015 | 1/2016 | 4/2016 | 7/2016 | 10/2016 | 1/2017 | 4/2017 | 7/2017 | 10/2017 | 1/2018 | 4/2018 | 7/2018 | 10/2018 | 1/2019 | 4/2019
Projected Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
# of Housing Units (Quarterly Projection) | 0 | [12 empty] | 1
Actual Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
# of Housing Units (Populated from QPR Reporting) | 0
Safe Rooms | 7/2012 | 10/2012 | 1/2013 | 4/2013 | 7/2013 | 10/2013 | 1/2014 | 4/2014 | 7/2014 | 10/2014 | 1/2015 | 4/2015 | 7/2015 | 10/2015 | 1/2016 | 4/2016 | 7/2016 | 10/2016 | 1/2017 | 4/2017 | 7/2017 | 10/2017 | 1/2018 | 4/2018 | 7/2018 | 10/2018 | 1/2019 | 4/2019
Projected Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
# of Housing Units (Quarterly Projection) | 0 | [9 empty] | 1 | 1 | 1
Actual Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
# of Housing Units (Populated from QPR Reporting) | 0
Residential Rehab and Reconstruction | 7/2012 | 10/2012 | 1/2013 | 4/2013 | 7/2013 | 10/2013 | 1/2014 | 4/2014 | 7/2014 | 10/2014 | 1/2015 | 4/2015 | 7/2015 | 10/2015 | 1/2016 | 4/2016 | 7/2016 | 10/2016 | 1/2017 | 4/2017 | 7/2017 | 10/2017 | 1/2018 | 4/2018 | 7/2018 | 10/2018 | 1/2019 | 4/2019
Projected Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 6 | 11 | 16 | 21 | 25 | 28 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30
# of Housing Units (Quarterly Projection) | 0 | [5 empty] | 0 | 1 | 5 | 5 | 5 | 5 | 4 | 3 | 2
Actual Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
# of Housing Units (Populated from QPR Reporting) | 0
Public Facilities | 7/2012 | 10/2012 | 1/2013 | 4/2013 | 7/2013 | 10/2013 | 1/2014 | 4/2014 | 7/2014 | 10/2014 | 1/2015 | 4/2015 | 7/2015 | 10/2015 | 1/2016 | 4/2016 | 7/2016 | 10/2016 | 1/2017 | 4/2017 | 7/2017 | 10/2017 | 1/2018 | 4/2018 | 7/2018 | 10/2018 | 1/2019 | 4/2019
Projected Facilities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
# of Public Facilities (Quarterly Projection) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual Facilities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
# of Public Facilities (Populated from QPR Reporting) | 0
Quarterly Projections by Activity Type:
Acquisition, construction,reconstruction of public facilities
# of Public Facilities | 0 | [8 empty] | 1 | 1 | 1
Construction/reconstruction of water lift stations
# of Public Facilities | 0
Construction/reconstruction of water/sewer lines or systems
# of Public Facilities | 0 | [10 empty] | 3
Dike/dam/stream-river bank repairs
# of Public Facilities | 0
Rehabilitation/reconstruction of public facilities
# of Public Facilities | 0
Economic Development | 7/2012 | 10/2012 | 1/2013 | 4/2013 | 7/2013 | 10/2013 | 1/2014 | 4/2014 | 7/2014 | 10/2014 | 1/2015 | 4/2015 | 7/2015 | 10/2015 | 1/2016 | 4/2016 | 7/2016 | 10/2016 | 1/2017 | 4/2017 | 7/2017 | 10/2017 | 1/2018 | 4/2018 | 7/2018 | 10/2018 | 1/2019 | 4/2019
Projected Jobs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
# of Jobs Created/Retained (Quarterly Projection) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual Jobs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
# of Jobs Created/Retained (Populated from QPR Reporting) | 0
# of Permanent Jobs Created | 0
# of Permanent Jobs Retained | 0
Public Infrastructure | 7/2012 | 10/2012 | 1/2013 | 4/2013 | 7/2013 | 10/2013 | 1/2014 | 4/2014 | 7/2014 | 10/2014 | 1/2015 | 4/2015 | 7/2015 | 10/2015 | 1/2016 | 4/2016 | 7/2016 | 10/2016 | 1/2017 | 4/2017 | 7/2017 | 10/2017 | 1/2018 | 4/2018 | 7/2018 | 10/2018 | 1/2019 | 4/2019
Projected Linear Feet of Public Improvements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6529 | 6529 | 6529 | 6529 | 6529 | 6529 | 6529 | 6529 | 6529 | 6529 | 6529 | 6529 | 6529 | 6529 | 6529 | 6529 | 6529
# of Linear Feet of Public Improvements (Quarterly Projection) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual Linear Feet of Public Improvements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
# of Linear Feet of Public Improvements (Populated from QPR Reporting) | 0
Quarterly Projections by Activity Type:
Construction/reconstruction of water/sewer lines or systems
# of Linear Feet of Public Improvements | 0 | [10 empty] | 6529
Dike/dam/stream-river bank repairs
# of Linear Feet of Public Improvements | 0
Rehabilitation/reconstruction of a public improvement
# of Linear Feet of Public Improvements | 0